## Product Backlog
Product Name: | Champion Amenity of Supercomputer Assembly (CASA) | [6 empty] | Complete Fields in Green!!!
Team ID: | Snow Lepord
| Team Member Name | [5 empty] | Initials | Student ID
Required | Ali Senkayi | [5 empty] | AKS
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 24 |  |  |  | Total | Total number of features (in column H)
1 | 19 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 19 | 0 |  |  | 2 | Total features left at the end of Sprint #2
3 | 8 | 11 |  |  | 3 | ...and so on
4 | 7 | 1
5 | 6 | 1
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
[5 empty] | Sprint to which Feature is Assigned |  |  | Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly | Validate the email address (lightly)
OPT | 2 | 1 |  | 3 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product | Validate that the cost is not negative
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
STORE | 5 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Provide a central collection of the above data | Create and manage information to run my store efficiently
WIN | 6 | 2 |  | 13 | 2 | Finished in Sprint 3 | Sales Staff | Add a GUI main window with menubar | Use it more easily | Recommend baselining Nim from Lecture 12
INSCU | 7 | 2 |  | 5 | 2 | Finished in Sprint 3 | Sales Staff | Insert new Customers via a sequence of dialogs | Do everything within the GUI | Recommend JOptionDialog from Lecture 13
INSOP | 8 | 2 |  | 3 | 2 | Finished in Sprint 3 | Sales Staff | Insert new Options via a sequence of dialogs | Do everything within the GUI
INSCO | 9 | 2 |  | 5 | 2 | Finished in Sprint 3 | Sales Staff | Insert new Computers via a sequence of dialogs | Do everything within the GUI
DISP | 10 | 2 |  | 5 | 2 | Finished in Sprint 3 | Sales Staff | List data (customers, options, and computers separately) in the main window display | Access the data directly in the window | You’ll need a View menu for this, and perhaps a JLabel in the main window center section
TOOLB | 11 | 2 |  | 8 | 2 | Finished in Sprint 3 | Sales Staff | Add a simple toolbar to the main window | Use the app with pushbutton convenience | Part of the Nim baseline. Create your own icons or find some online.
ABOUT | 12 | 3 |  | 2 | 2 | Finished in Sprint 3 | Director | (If needed) Provide a simple text-only About dialog | Avolid a lawsuit | (If needed) Rewrite the text from Nim's implementation to comply with toolbar icon license obligations
ABOSK | 13 | 3 |  | 5 | 3 | In Work | Director | Provide About dialog with sketch as or around a bitmap logo for aesthetics and documenting licenses | Impress users | Recommend a subclass of JPanel from Lecture 15 with a simple diagram plus Jlabels in one or more JPanels with program information
SAVE | 14 | 3 |  | 13 | 3 | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save (via method) and reload (via constructor) each object from a provided stream
NEW | 15 | 3 |  | 1 | 3 | Finished in Sprint 3 | Manager | Create a new, empty store | Start new franchises | This is as easy as “new Store” with a name
SAVAS | 16 | 3 |  | 5 | 3 | Finished in Sprint 3 | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use JfileChooser
LOAD | 17 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use JfileChooser
INSOR | 18 | 4 |  | 5 |  |  | Sales Staff | Insert new Orders via a sequence of dialogs | Do everything within the GUI
OCOST | 19 | 4 |  | 5 | 4 | Finished in Sprint 4 | Sales Staff | Calculate and display total cost of order | Know how much to charge the customer
DISP2 | 20 | 4 |  | 2 |  |  | Sales Staff | List ORDERS in the main window display | Access the order data | This is a minor change
DCUST | 21 | 4 |  | 13 |  |  | Sales Staff | Replace sequencial dialogs with custom dialogs | Enter data more quickly | More practice with custom dialogs (just Insert Customer & Option here) - INCLUDE icon used on button in the dialog
GEN | 22 | 5 |  | 8 | [5 empty] | Use a generic in some way (TBD)
UNIQ | 22 | 5 |  | 5 |  |  | Manager | Avoid duplicate data entry | Keep the database clean | Require a Set with hashCode implementations for store classes
SPEC | 18 | 5 |  | 13 |  |  | Customer | Store and display type-specific data | Ensure I purchase the correct product | Use inheritance with polymorphism
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
SCROL |  |  |  | 5 |  |  | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR |  |  |  | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR |  |  |  | 8 |  |  | Manager | Add a status bar to the main window | Better track status of messages | A stack of messages that can be reviewed would be worth more!
DTAIL |  |  |  | 21 |  |  | Customer | Provide a detail view of a product type info in the main window | Provide additional info about each product
PIX |  |  |  | 13 |  |  | Customer | {Prerequisite: DTAIL} Include a picture of the product in its detail view | Save a thousand words | The image can be a file. Store the filename in Option, and load from disk when required

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2023-02-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-02-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 22
Day 1 Left | 22 | 0
Day 2 Left | 22 | 0
Day 3 Left | 22 | 0
Day 4 Left | 17 | 5
Day 5 Left | 13 | 4
Day 6 Left | 9 | 4
Day 7 Left | 7 | 2
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2 | CUST |  | Write Customer class | In Work
3 | CUST |  | Copy build.xml into repo and test compile Customer | Completed Day 4
4 | CUST |  | Add Customer to GitHub | Completed Day 4 | git push
5 | OPT |  | Write Option class | In Work
6 | OPT |  | Add Option to GitHub | Completed Day 4 | git push
7 | CUST |  | Write Computer Class Aggregation | In Work
8 | CUST |  | Add Customer, Option, & Computer to GitHub | Completed Day 4 | git push
9 | CUST |  | Add Customer, Option, & Computer to GitHub | Completed Day 4 | git push
10 | ORDER |  | Write Order class | In Work
11 | ORDER |  | Add Order to GitHub | Completed Day 5 | git push
12 | ORDER |  | Add Order & Computer revisions to GitHub | Completed Day 5
13 | CUST |  | Add Customer revisions to to GitHub | Completed Day 5 | git push
14 | CUST |  | Write Customer class REGEX | Completed Day 5
15 | CUST |  | Add Customer REGEX revisions to GitHub | Completed Day 6 | git push
16 | CUST |  | Add Customer equals(Object o) revisions to GitHub | Completed Day 6 | git push
17 | OPT |  | Add neg., throw IllegalArgumentException Option to GitHub | Completed Day 6
18 | OPT |  | Add Option equals(Object o) revisions to GitHub | Completed Day 6 | git push
19 | DESKT |  | Add Computer equals(Object o) revisions to GitHub | Completed Day 7 | git push
20 | STORE |  | Add Store to GitHub | In Work
21 | STORE |  | Add TestStore to GitHub | In Work
22 | STORE |  | TestStore completed | Completed Day 7 | NO data displayed ~ java TestStore
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2023-02-28 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 7
Day 1 Left | 7 | 0
Day 2 Left | 7 | 0
Day 3 Left | 7 | 0
Day 4 Left | 7 | 0
Day 5 Left | 7 | 0
Day 6 Left | 7 | 0
Day 7 Left | 6 | 1
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2 | WIN |  | Add git commit -m "P06 add store gui ~ 3/6/23 12:36 PM" | In Work
3 | DISP |  | Add git commit -m "P06 Trial Run 3/6/23” | In Work
4 | INSCU |  | Write Listeners Customer | In Work
5 | INSCU |  | Add Cust to GitHub ~ 3/6/23 12:36 PM" | In Work
6 | CUST |  | Add Cust to GitHub ~ 3/6/23 12:36 PM" | Completed Day 7
7 | INSCO |  | add INSCO to GitHub ~ 3/6/23" | In Work
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2023-03-07 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 19
Day 1 Left | 19 | 0
Day 2 Left | 19 | 0
Day 3 Left | 18 | 1
Day 4 Left | 18 | 0
Day 5 Left | 14 | 4
Day 6 Left | 13 | 1
Day 7 Left | 13 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2 | SAVE |  | git commit -m "P07 Trial Run GOOD 3/16/2023 5:08 AM" | Completed Day 3 | git push
3 | SAVE |  | Save (via method) & reload (via constructor) each obj. Cust. | In Work
4 | SAVE |  | git commit -m "P07 Trial Run GOOD 3/17/2023 2:54 AM" | In Work | git push
5 | SAVE |  | Save (via method) & reload (via constructor) each obj. Opt. | In Work
6 | SAVE |  | git commit -m "P07 Save/Load Option 3/17/2023 1:15 PM" | In Work | git push
7 | SAVE |  | Save (via method) & reload (via constructor) each obj. Opt. | In Work
8 | SAVE |  | git commit -m "P07 Save/Load Order 3/18/2023 1:15 AM" | In Work | git push
9 | SAVE |  | Save (via method) & reload (via constructor) each obj. Store & Order | In Work
10 | SAVE |  | git commit -m "P07 Save/Load Order 3/19/2023 2:37 AM" | In Work | git push
11 | LOAD |  | Write – “Load” data form a specified file (File > Open) | In Work
12 | LOAD |  | Add (File > Open) to GitHub | Completed Day 5 | git push
13 | SAVAS |  | Write – “Save” data to a specified file (File > Save As) | In Work
14 | SAVAS |  | Add (File > Save As) to GitHub | Completed Day 5 | git push
15 | SAVE |  | Finish write – “Save” the data to a default file (File > Save) | Completed Day 5
16 | SAVE |  | Add (File > Save) to GitHub | Completed Day 5 | git push
17 | NEW |  | Add to GitHub - Create a new, empty store | Completed Day 6 | git push
18 | ABOSK |  | Write – Design Graph | In Work | git push
19 | ABOSK |  | Write – Design Graph | In Work
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Note on D28: git commit -m "P07 Load (File > Open) 3/19/2023 5:37 PM"
Note on D30: git commit -m "P07 Save (File > Save As) 3/19/2023 9:10 PM"
Note on D32: git commit -m "P07 Save (File > Save) 3/19/2023 9:10 PM"
Note on D33: git commit -m "P07 Create a new, empty store 3/20/2023 3:15 PM"
Note on D34: git commit -m "P07 Create Graphics 3/20/2023 10:12 PM"
Note on D35: git commit -m "P07 Last Item - Create Graphics 3/21/2023 12:57 AM"

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2023-04-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 2
Day 1 Left | 2 | 0
Day 2 Left | 2 | 0
Day 3 Left | 2 | 0
Day 4 Left | 2 | 0
Day 5 Left | 2 | 0
Day 6 Left | 2 | 0
Day 7 Left | 1 | 1
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2 | OCOST |  | git commit -m "P10 Trial Run Calculate total cost of order” | Completed Day 7
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2023-04-18 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-25
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 6 | BONUS | Complete Fields in Green!!!
Start on | 2023-04-25 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-05-02
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
NOTE: This sprint is entirely OPTIONAL – no points will be lost if you ignore it
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84